## Slide 1: Engagement Status Report
May 2026
5/1/2026
F5 FinOps Data Platform

## Slide 2: F5 FinOps Data Platform – Week of 5/1
Key Activities Completed This Week | Key Activities Planned for Next Week | Critical Open Questions/ Issues
Activity Type 1 Completed Sub-Activity 1 Completed Sub-Activity 2 Activity Type 2 Completed Sub-Activity 1 Completed Sub-Activity 2 Completed Activity 1 Completed Activity 2 Completed Activity 3 | Activity Type 1 Planned Sub-Activity 1 Planned Sub-Activity 2 Activity Type 2 Planned Sub-Activity 1 Planned Sub-Activity 2 Planned Activity Planned Activity Planned Activity | Data Access Permissions requirements (who can see what data) Understanding Export requirements for AWS and Azure Finalizing details on MVP Architecture
ID | Risk / Assumption / Issue / Decision | Mitigation / Impact | Severity | Owner | Resolution Date
1 | Currently Missing JIRA Access | Will have trouble billing out a functional backlog without JIRA Access, We will start using other templates and soon confluence Service now ticket has been submitted – PDI0237219 | Low | Torin | 5/8
2 | Getting access to necessary data sources, tools, etc.. Is critical to complete within this next week, specifically for AWS; for us to complete the foundation work by the 22nd. | We are submitting service now requests as soon as we get them. Meeting with Kaylan today to start defining architecture in detail Meeting with Prasant to determine AWS Export bucket is set up for early next week. | High | Torin | 5/8
Current Status | Overall Status | Schedule | Budget | Scope
 | G | Y | G | G
Scope Summary | Establish a multi-cloud FinOps foundation across AWS, Azure, and GCP to provide automated, business-aligned visibility into cloud spend, usage, and optimization opportunities. Phases 1 and 2 will prioritize maturity in the primary renewal cloud (AWS), while delivering structured Ingestion, normalization, and a baseline visibility across Azure and GCP.
Status Overview | Overall status is Green status on track. I’ve made schedule yellow, because next week will be critical to complete Project Definition and Design. No major concerns about us being able to do that, but wanted to identify the risk.

## Slide 3
Priority | Milestone | Description | Status | ADR Date | Delivery Date
1 | MVP Definition & Feature Capture | Define and document the Minimum Viable Product (MVP), including functional requirements, in‑scope and out‑of‑scope capabilities, project goals, and an initial effort estimate. This milestone establishes a shared understanding of what will be delivered in the MVP and sets clear boundaries for MVP architecture, development and scope. Additionally, the identification of future features will be captured. | In progress | 5-May | 8-May
2 | MVP Architecture Complete | Align and Finalize the MVP technical architecture prior to TMA and ARB approval finalization. This milestone confirms that the architecture is fit for purpose, understood by stakeholders, and ready for approvals. | In progress | 6-May | 6-May
3 | Backlog initialization | Translate the approved MVP definition into a structured delivery backlog. This includes defining epics, features, and initial engineering‑ready stories, as well as establishing and aligning on the Definition of Ready (DoR) and Definition of Done (DoD) to support consistent and predictable delivery. Includes future state features to support roadmap. | Not Started | 15-May | 15-May
4 | Tech Apprv’l Comp. | TMA, ARB, Completed and validated for MVP architecture | Started | 8-May | 8-May
5 | FinOps Data Platform Roadmaps | Develop a forward‑looking roadmap that outlines future platform capabilities beyond the MVP into future work. This milestone provides clarity on near‑term priorities and sequencing (approximately the next two months), while also communicating longer‑term direction to support planning, alignment, and expectation setting. | Not Started | 15-May | 15-May
6 | Foundations Buildout | Establish the core technical foundations required to support the FinOps data platform for AWS. This includes provisioning and configuring the SF WH environment, setting up DevOps and version control workflows, validating environments, and confirm successful data ingestion from AWS billing sources. | Started | 6-May | 22-May
9 | Feedback Workshop 1st | Conduct structured stakeholder workshops to review a working demo of the solution, gather feedback, and validate direction. Feedback will be documented, prioritized, and used to confirm readiness for the next phase or to inform targeted refinements. | Not Started | NA | 22-May
FinOps Data Platform – 4 Week Project Milestones

## Slide 4
Priority | Milestone | Description | Status | ADR Date | Delivery Date
7 | MVP Sources Integrated - Azure | Integrate Azure cost and usage data into the platform and validate that the data is successfully ingested, processed, and visualized. This milestone ensures Azure data can be used reliably for FinOps reporting and analysis within the MVP. | Not Started | TBD | TBD
8 | MVP Sources Integrated - GCP | Integrate Google Cloud Platform (GCP) cost and usage data into the platform and confirm successful ingestion and visualization. This enables multi‑cloud visibility and supports cross‑provider comparison within the MVP. | Not Started | TBD | TBD
10 | Agent Strategy Implemented | Implement and operationalize the defined agent strategy, including persona‑based usage patterns, restrictions, and governance controls. This milestone ensures agent capabilities are applied consistently, safely, and in alignment with agreed‑upon roles and responsibilities. | Not Started | TBD | TBD
11 | MVP Complete | Deliver a complete MVP that is ready for controlled rollout and validation with a selected group of power users. The solution provides usable insights, supports the intended FinOps use cases, and is prepared for structured feedback, iteration, or broader adoption. | Not Started | NA | TBD
FinOps Data Platform – 10 Week Project Milestones
Notes: Workstream, Priority Order, ADR date, Milestone, Milestone description

## Slide 5: FinOps Data Platform - Week by Week
Week | 4/27 – 5/1 | 5/4 – 5/8 | 5/11 – 5/15 | 5/18 – 5/22
Project Initialization | App/Tool Access – 4/30 JIRA/Confluence LucidChart - Provisioned Establish Ways of Working – In Progress Onboarding training – In progress Confluence Space Creation and Structure setup | JIRA Board Creation and Setup Any additional data access requirements identified and requested | Additional TBD? | Team Onboarding Preparation
Product Definition | Intro Meeting with Ankit - 4/28 - Done Start: Persona Definition - 4/27 – In Progress Start: Stakeholder Interviews - 5/1 - TBD Share Requirements Templates – 4/28 - Done Product Definition Initial Requirements Discussion – 4/29 - Done FinOps Team | Finalize: Persona Definitions Finalize: Create initial Epic and Features Align on Data Presentation Layer Reqs Needs review Check w/ Digital, Data, FinOps, & PE teams | Alignment Check on Project Goal KPI Definitions Workshops w/ FinOps, Product, Data, and Digital teams Start: Creating Readout Finalize: Stakeholder Interviews | 2 Week Backlog Finalize: Readout Review Readout
Technical Design | Architectural Alignment Team Kickoffs – Digital, Data, FinOps, Start: Technical design documentation Billing API structure ( AWS/Azure/GCP ) Available cost and usage data sources Document enterprise setup ( accounts, subscriptions, org structure Validate data access and permissions | Continue: Technical design documentation Data ingestion approach defined (Billing API and/or exports ) End to end data flow and system integration points defined and documented Snowflake setup and access aligned ( roles, schemas, ownership) Finalize: dashboard requirements | Finalize: Data ingestion strategy and data pipeline design Dashboard layout / KPI visualization structure defined Data model and transformation logic defined Technical design refined based on final requirements End to end architecture documented and reviewed Cortex code approach defined for data processing and optimization | Data pipeline development initiated Start: core data ingestion implementation Review and validate initial dataset Start: Initial data transformation Start: data validation framework implementation Cortex code-based processing implementation begins